## Sprint 1
Spring Backlog
Story Name | Point | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
Sprint 1
Create Database | 4 | Nam | 2019-07-03 | 2019-08-03
Login | 2 | Vinh | 2019-11-03 | 13/3/2019
Register | 2 | Nam | 2019-11-03 | 2019-11-03
Interface | 3 | Vinh | 2019-09-03 | 2019-10-03

## Sprint 2
Sprint Backlog
Story ID | Story Name | Point | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
Sprint 2
1 | Create a Terms and Conditions for student | 3 | Vinh | 20/03/2019 | 25/03/2019 | 21/3/2019 | 26/03/2019 | 3
2 | Create maintains system data to maintains data | 6 | Vinh | 14/03/2019 | 19/03/2019 | 14/03/2019 | 20/03/2019 | 6
3 | Create analysis system which can show information | 5 | Nam | 20/03/2019 | 25/03/2019 | 21/3/2019 | 26/03/2019 | 5
4 | Create decentralization system | 3 | Vinh | 26/03/2019 | 27/03/2019 | 27/03/2019 | 28/03/2019 | 3

## Sprint 3
Sprint Backlog
Story ID | Story Name | Point | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
Sprint 3
5 | Create form to set date or deadline to submit entries. | 3 | Nam | 2019-05-04 | 2019-11-04
6 | Create a email response system for notification to Faculty’s Marketing Coordinator | 5 | Vinh | 29/03/2019 | 2019-04-04
7 | Create account for Marketing Manager to oversee the process | 3 | Vinh | 2019-05-04 | 2019-07-04
8 | All student who submit their contributions will have mail and the Marketing Coordinator can be able to interact with the students follow email. | 5 | Nam | 29/03/2019 | 2019-04-04

## Sprint 4
Sprint Backlog
Story ID | Story Name | Point | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
Sprint 4
9 | Create a form to submit word document | 5 | Vinh | 2019-12-04 | 17/04/2019 | 2019-12-04 | 18/04/2019 | 5
10 | Create a form which can upload high quality images | 4 | Nam | 18/04/2019 | 20/4/2019 | 19/04/2019 | 20/04/2019 | 4
11 | Create a guess account for students. | 5 | Vinh | 2019-12-04 | 17/04/2019 | 2019-12-04 | 18/04/2019 | 5
12 | View for Marketing Manager | 5 | Nam | 13/4/2019 | 15/4/2019 | 13/04/2019 | 16/04/2019 | 5

## Sprint 5
Story ID | Story Name | Point | Name of Dev | Start Date | End Date | Act Start Date | Act End Date | Act Point | Notes
Sprint 5
| Group Report | 4 | Huy, Hao | 21/04/2019 | 25/04/2019 | 21/04/2019 | 25/04/2019 | 4
| Testing | 4 | Nam, Vinh | 21/04/2019 | 25/04/2019 | 21/04/2019 | 25/04/2019 | 4
13 | Create download function with zip file. | 5 | Vinh | 21/04/2019 | 22/04/2019 | 21/04/2019 | 22/04/2019 | 5